## 24 May update
| May |  | June |  |  |  | July |  |  |  | August
| 3 week | 4 week | 1 week | 2 week | 3 week | 4 week | 1 week | 2 week | 3 week | 4 week | 1 week | 2 week | 3 week | 4 week
tools specification (questionnaire and sampling) | done
CATI/F2F enumerators' training |  | ongoing
CATI pilot
CATI HH data collection
CATI key informants' interviews
CATI preliminary analysis
F2F HH data collection
F2F preliminary analysis
CFSAM field mission
presentation of preliminary finding (internal)
report drafting
Report cleared by FAO/WFP
Report sent to Government by FAO
Post report on the web